## Sheet1
PMQuizzez Project Cost Estimate
Prepared by: Poojitha Singam | Date: | 2019-05-24
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 231497 | 25.45%
1.1 Project manager | 600 | 110 | 66000
1.2 Project team members | 1700 | 75 | 127500
Contractors (10% of software development and testing) |  |  | 37997
2. Hardware |  |  |  | 50100 | 5.507%
2.1 Handheld devices | 50 | 600 | 30000
2.2 Servers | 3 | 6700 | 20100
3. Software |  |  |  | 349600 | 38.43%
3.1 Licensed software | 80 | 120 | 9600
3.2 Software development* |  |  | 340000
4. Testing (10% of total hardware and software costs) |  |  | 39970 | 39970 | 4.394%
5. Training and Support |  |  |  | 86920 | 9.555%
5.1 Trainee cost | 65 | 320 | 20800
5.2 Travel cost | 8 | 390 | 3120
5.3 Project team members | 900 | 70 | 63000
6. Reserves (20% of total estimate) |  |  | 151617.4 | 151617.4 | 16.67%
Total project cost estimate |  |  |  | 909704.4
* See software development estimate

## Sheet2
* Software development
Contractor labor estimate | 1500 | 110 | 165000
Project team member estimate | 1150 | 90 | 103500
Total labor estimate |  |  | 268500
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 7 | 4 | 28
External interface files | 3 | 8 | 24
External outputs | 5 | 2 | 10
External queries | 1 | 3 | 3
Logical internal tables | 4 | 10 | 40
Total function points |  |  | 105
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 4830
Productivity *KSLOC^Penalty (person months) | 20.6768
Total labor hours (140 hours/month) | 2481.2188
Cost/labor hour ($110/hour) | 120
Total software development estimate | 297746.2552